## Sheet1
Risk Register
Risk ID | Risk Description | Risk Type | Impact Level Rate 1 (LOW) to 5 (HIGH) | Likelihood Level Rate 1 (LOW) to 5 (HIGH) | Priority Level Impact x Likelihod Address the highest first. | Risk Treatment Options | Corrective Action | Status | Owner | Date Identified | Last Reviewed | Additional Notes
INC - 001 | There is a risk of unauthorized access to core business applications due to weak identity and access management controls, leading to data breach or fraud. | IT / Cyber | 5 | 4 | 20 | Mitigate | MFA enabled, quarterly access review, SIEM monitoring | Open | Kavita | 2025-12-10 | 2025-02-12
INC - 002 | Risk of penalties and reputational damage due to non-compliance with applicable data protection regulations (e.g., local privacy laws). | Compliance | 5 | 3 | 15 | Escalate | Privacy policy, periodic compliance audits | In-progress | Mohit | 10-13-2025 | 2025-02-12
INC - 003 | Risk of business interruption due to failure or downtime of critical outsourced service providers. | Third-Party | 4 | 4 | 16 | Mitigate | SLA clauses, BCP review, redundancy vendor arrangement | Closed | Kavita | 10-14-2025 | 2025-02-12
INC - 004 | Risk of material misstatement in financial reports due to inadequate review controls or system errors. | Financial | 5 | 4 | 20 | Accept | Internal audit review | Open | Lata | 10-15-2025 | 2025-02-12
INC - 005 | Risk of operational disruption due to high attrition in specialized or leadership roles. | Strategic | 4 | 3 | 12 | Avoid | Succession planning, retention bonuses, cross-training | In-progress | Arun | 10-16-2025 | 2025-02-12
INC - 006 | Risk of credential compromise or financial loss due to phishing attacks targeting employees. | IT / Cyber | 5 | 4 | 20 | Mitigate | Email filtering, phishing simulations, awareness training | In-progress | Arun | 10-17-2025 | 2025-02-12
INC - 007 | Risk of inability to resume critical operations within RTO during natural disasters or infrastructure outages. | Operational | 5 | 2 | 10 | Transfer | DR site, annual BCP testing | Closed | Lata | 10-18-2025 | 2025-02-12
INC - 008 | Risk of sensitive customer data exposure due to improper cloud storage configuration | IT / Cyber | 5 | 4 | 20 | Mitigate | Encryption, access control | Open | Mohit | 10-19-2025 | 2025-02-12
INC - 009 | Risk of short-term liquidity constraints due to delayed client payments impacting operational cash flow | Financial | 4 | 3 | 12 | Accept | Credit control policy | Open | Kavita | 10-20-2025 | 2025-02-12

## Scale and Key
RISK HEATMAP
|  |  | LIKELIHOOD | 5 | 5 | 10 | 15 | 20 | 25
|  |  |  | 4 | 4 | 8 | 12 | 16 | 20
|  |  |  | 3 | 3 | 6 | 9 | 12 | 15
|  |  |  | 2 | 2 | 4 | 6 | 8 | 10
|  |  |  | 1 | 1 | 2 | 3 | 4 | 5
[5 empty] | 1 | 2 | 3 | 4 | 5
IMPACT
| RISK IMPACT | [8 empty] | RISK LIKELIHOOD
| 1 | Very Low | [7 empty] | 1 | 1% - 20%
| 2 | Low | [7 empty] | 2 | 21% - 40%
| 3 | Moderate | [7 empty] | 3 | 41% - 64%
| 4 | High | [7 empty] | 4 | 65% - 80%
[10 empty] | 5 | 80% - 100%